## PROJECT PLAN ORIGINAL
[5 empty] | Date | 2021-01-26 | 2021-02-02 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2021-05-11
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress
Project Initiation | Discuss project proposals | ALL | 2021-01-23 | 2021-01-27
| Confirm Project Team Roles | ALL | 2021-01-23 | 2021-01-27
| Develop two business cases | Vihan Parmar | 2021-02-03 | 2021-02-07
| Develop Project Initiation Document (PID) | Vihan Parmar | 2021-02-02 | 2021-02-07
| Produce initial Project Plan, RACI | Vihan Parmar | 2021-02-09 | 2021-02-11
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Mady Dembele | 2021-02-16 | 2021-02-23
| Produce Context Diagram, Define System Interfaces | Roneil Boodram | 2021-02-16 | 2021-02-23
| Define Business Requirements | Lang Gong | 2021-02-16 | 2021-03-23
| Agree to System Requirements types | All | 2021-02-16 | 2021-03-23
| Define Functional Decomposition | All | 2021-02-27 | 2021-03-06
| Produce RCT document | Roneil Boodram | 2021-02-23 | 2021-03-02
| Decide which features to implement this semester | All | 2021-03-06 | 2021-03-13
| Produce analysis diagrams (UML, DFD) | Lang Gong | 2021-03-02 | 2021-03-09
| Define functional requirements (User Stories) 1. End-users must be able to create an account(s) 2. End-users must be able to modify their account(s) 3. Users can check the status of shipment 4. End-users must be able to request refund for disputed charge (refund is subject to review and approval) 5. Users can receive the receipts of order information. 6. Users can receive the tracking numbers and view the details about product delivery at any time. 7. User should be able to save their preferred items in a cart. 8. Users should be able to make online payments. 9. User can review previous purchase history. 10. User has ability to enter/modify the delivery address 11. User has ability to save favorite stores' locations 12. User has ability to read the product detail information 13. User has ability to add/remove items to/from the cart 14. User has ability to clear all items from the cart 15. User has ability to cancel the order before it is prepared for shipping 16. User has ability to communicate with the delivery person 17. Product Arrival notification (If the product is out of stock, the user can choose to follow this product, once this product is restocked, a notification will be sent to the user). | Roneil Boodram | 2021-03-02 | 2021-03-09
| Update Project Plan with additional requirements tasks | Vihan Parmar | 2021-03-02 | 2021-03-09
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Jevon Cowell, George Lopez | 2021-04-06 | 2021-04-13
| Database Design (ERD, Table spec) | Jevon Cowell, George Lopez | 2021-03-30 | 2021-04-06
| System Interface Design | Jevon Cowell, George Lopez | 2021-04-06 | 2021-04-13
| User interface design | Jevon Cowell, George Lopez | 2021-04-13 | 2021-04-20
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | TBD | 2021-03-02 | 2021-04-20
| Coding & Implemenation | TBD | 2021-03-02 | 2021-04-20
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Maisha Masnoon, Tianqi Han | 2021-03-27 | 2021-04-24
| Evaluate Features to be Tested | Maisha Masnoon, Tianqi Han | 2021-03-27 | 2021-04-24
| Design Test Cases | Maisha Masnoon, Tianqi Han | 2021-03-27 | 2021-04-03
| Execute Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-03 | 2021-04-10
| Anaylze Test Results | ALL | 2021-04-10 | 2021-04-17
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2021-05-01 | 2021-05-08

## UPDATED PROJECT PLAN
Color Coding |  |  | Completed |  |  | SPRING 2020 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Date | 2021-01-26 | 2021-02-02 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss Project Proposals |  | ALL | 2021-01-23 | 2021-01-26 | 100%
| Confirm Project Team Roles |  | ALL | 2021-01-23 | 2021-01-26 | 100%
| Develop Two Business Cases |  | Vihan Parmar | 2021-01-26 | 2021-02-02 | 100%
| Develop Project Initiation Document (PID) |  | Vihan Parmar | 2021-02-02 | 2021-02-07 | 100%
| Refined Initial Project Plan, RACI |  | Vihan Parmar | 2021-02-09 | 2021-02-11 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Develop and Complete Application Home Page |  | Jevon Cowell, George Lopez | 2021-02-09 | 2021-02-14 | 100%
| Produce BRM Diagram, Define User Roles |  | Mady Dembele | 2021-02-16 | 2021-02-23 | 100%
| Produce Context Diagram, Define System Interfaces |  | Roneil Boodram | 2021-02-16 | 2021-02-23 | 100%
| Update Project Plan With Additional Requirements Tasks |  | Vihan Parmar | 2021-02-16 | 2021-02-23 | 100%
| Define Business Requirements |  | Mady Dembele | 2021-02-16 | 2021-03-02 | 100%
| Agree to System Requirements Types |  | All | 2021-02-16 | 2021-03-02 | 100%
| Define Functional Decomposition |  | Lang Gong | 2021-02-23 | 2021-03-02 | 100%
| Produce RCT Document |  | Roneil Boodram | 2021-02-23 | 2021-03-02 | 100%
| Produce Analysis Diagrams (UML, DFD) |  | Lang Gong | 2021-03-02 | 2021-03-09 | 100%
| "Define functional requirements (User Stories) |  | Roneil Boodram | 2021-03-02 | 2021-03-09 | 100%
| Decide Which Features to Implement This Semester |  | All | 2021-03-06 | 2021-03-13 | 80%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Database Design (ERD, Table Spec) |  | Jevon Cowell, George Lopez | 2021-03-30 | 2021-04-06 | 100%
| Produce Physical Data-flow Diagram |  | Lang Gong | 2021-03-30 | 2021-04-06 | 100%
| Establish Github |  | All | 2021-03-30 | 2021-04-13 | 80%
| Architecture Design (2 Diagrams) |  | Jevon Cowell, George Lopez | 2021-04-06 | 2021-04-13 | 100%
| System Interface Design |  | Jevon Cowell, George Lopez | 2021-04-06 | 2021-04-13
| User Interface Design |  | Jevon Cowell, George Lopez | 2021-04-13 | 2021-04-20
MILESTONE 3: DESIGN COMPLETED
Implementation | 03.04 Sign Up | Produce Class and Sequence Diagrams (UML) | Jevon Cowell, George Lopez | 2021-04-13 | 2021-04-20 | 100%
|  | GUI & Functionality Detailed Design | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 100%
|  | Provide Code Executable Ready for Testing | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 100%
| 03.05 Sign In | Produce Class and Sequence Diagrams (UML) | Jevon Cowell, George Lopez | 2021-04-13 | 2021-04-20 | 100%
|  | GUI & Functionality Detailed Design | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 80%
|  | Provide Code Executable Ready for Testing | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 80%
| 03.06 Sign Out | Produce Class and Sequence Diagrams (UML) | Jevon Cowell, George Lopez | 2021-04-13 | 2021-04-20 | 100%
|  | GUI & Functionality Detailed Design | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 80%
|  | Provide Code Executable Ready for Testing | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 80%
| 05.03 Manage Orders (Make Edits) | Produce Class and Sequence Diagrams (UML) | Jevon Cowell, George Lopez | 2021-04-13 | 2021-04-20 | 100%
|  | GUI & Functionality Detailed Design | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 80%
|  | Provide Code Executable Ready for Testing | Jevon Cowell, George Lopez | 2021-03-02 | 2021-04-20 | 80%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Maisha Masnoon, Tianqi Han | 2021-04-20 | 2021-04-27 | 100%
| Evaluate Features to be Tested 1) End User-Account, 2) Shopping Cart |  | Maisha Masnoon, Tianqi Han | 2021-04-20 | 2021-04-22
| 03.04 Sign Up | Design Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-20 | 2021-04-23 | 100%
|  | Execute Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-21 | 2021-04-24 | 100%
|  | Anaylze Test Results | ALL | 2021-04-21 | 2021-04-25 | 100%
| 03.05 Sign In | Design Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-20 | 2021-04-23 | 80%
|  | Execute Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-21 | 2021-04-24 | 80%
|  | Anaylze Test Results | ALL | 2021-04-21 | 2021-04-25 | 80%
| 03.06 Sign Out | Design Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-20 | 2021-04-23 | 80%
|  | Execute Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-21 | 2021-04-24 | 80%
|  | Anaylze Test Results | ALL | 2021-04-21 | 2021-04-25 | 80%
| 05.03 Manage Orders (Make Edits) | Design Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-20 | 2021-04-23 | 80%
|  | Execute Test Cases | Maisha Masnoon, Tianqi Han | 2021-04-21 | 2021-04-24 | 80%
|  | Anaylze Test Results | ALL | 2021-04-21 | 2021-04-25 | 80%
| Update Project Plan with additional requirements tasks |  | Vihan Parmar | 2021-04-25 | 2021-04-27
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2021-05-01 | 2021-05-11