## R2 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Implement Core Functionality | 2021-11-13 | 2021-11-15 | 50% | Jevon Cowell , George Lopez
2 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Implement GUI | 2021-11-13 | 2021-11-15 | 80% | Jevon Cowell , George Lopez
3 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Crosscut Location Accuracy: Ensure that the location of driver/vendor/end-user are accurately reflected on mapping system. | 2021-11-13 | 2021-11-15 | 0% | Jevon Cowell , George Lopez
4 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Crosscut Field Validation: Ensure data can be entered into Cart screen | 2021-11-13 | 2021-11-15 | 50% | Jevon Cowell , George Lopez
5 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Crosscut Calculations: Ensure user can add items to their cart and the number of items in the Cart is calculated correctly as well as the price. | 2021-11-13 | 2021-11-15 | 80% | Jevon Cowell , George Lopez
6 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Crosscut Data Flow Out: Ensure data is flowing to Checkout Page | 2021-11-13 | 2021-11-15 | 50% | Jevon Cowell , George Lopez
7 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Use Case Specification | 2021-11-13 | 2021-11-15 | 100% | Roneil Boodram
8 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Core functionality | 2021-11-13 | 2021-11-15 | 100% | Roneil Boodram
9 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for GUI | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
10 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Core functionality | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
11 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Field Validation | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
12 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Calculations | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
13 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Data Flow Out | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
12 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Cache | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
13 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Exception Handling | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
14 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Create Test Case for Connectivity | 2021-11-13 | 2021-11-16 | 100% | Roneil Boodram
16 | R2 - I3 | 05. Shopping Cart | 5.02 | Manage Orders | Execute test cases and document the test execution log | 2021-11-15 | 2021-11-16 | 0% | Maisha Masnoon
17 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Implement Core Functionality | 2021-11-15 | 2021-11-16 | 100% | Jevon Cowell , George Lopez
18 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Implement GUI | 2021-11-15 | 2021-11-16 | 100% | Jevon Cowell , George Lopez
19 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Crosscut Connecttivity: Changes the behavior of the system in case the front end is disconnected from the back end | 2021-11-15 | 2021-11-16 | 100% | Jevon Cowell , George Lopez
20 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Crosscut Data Flow Out: Ensure data is flowing to View Order History Feature | 2021-11-15 | 2021-11-16 | 100% | Jevon Cowell , George Lopez
17 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Crosscut Cache: previous entries will be saved in cache. | 2021-11-15 | 2021-11-16 | 0% | Jevon Cowell , George Lopez
18 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Crosscut Exception Handle: exceptions thrown and logged if form post is successful. | 2021-11-15 | 2021-11-16 | 90% | Jevon Cowell , George Lopez
19 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Use Case Specification | 2021-11-09 | 2021-11-11 | 100% | Vihan Parmar
19 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Test Case for Core functionality | 2021-11-15 | 2021-11-18 | 100% | Lang Gong
20 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Test Case for GUI | 2021-11-15 | 2021-11-18 | 100% | Lang Gong
21 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Test Case for Connectivity | 2021-11-15 | 2021-11-18 | 100% | Lang Gong
22 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Test Case for Data Flow Out | 2021-11-15 | 2021-11-18 | 100% | Lang Gong
23 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Test Case for Cache | 2021-11-15 | 2021-11-18 | 100% | Lang Gong
24 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Create Test Case for Exception Handling | 2021-11-15 | 2021-11-18 | 100% | Lang Gong
25 | R2 - I3 | 05 Shopping Cart | 5.03 | Cancel Order | Execute test cases and document the test execution log | 2021-11-13 | 2021-11-18 | 0% | Maisha Masnoon
26 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Implement Core Functionality | 2021-11-17 | 2021-11-18 | 80% | Jevon Cowell , George Lopez
27 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Implement GUI | 2021-11-17 | 2021-11-18 | 80% | Jevon Cowell , George Lopez
28 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Crosscut Security: User input must be sanitized. Sensitive data sent will be hashed for data transit. | 2021-11-17 | 2021-11-18 | 0% | Jevon Cowell , George Lopez
29 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Crosscut Calculations: Ensures effectiveness of methods for User Valdiation.. Payment validation. | 2021-11-17 | 2021-11-18 | 0% | Jevon Cowell , George Lopez
30 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Crosscut Connecttivity: Changes the behavior of the system in case the front end is disconnected from the back end | 2021-11-17 | 2021-11-18 | 70% | Jevon Cowell , George Lopez
31 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Crosscut Data Flow In: Ensure data is flowing into generate receipt Core Feature | 2021-11-17 | 2021-11-18 | 100% | Jevon Cowell , George Lopez
32 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Crosscut Exception Handle: exception thrown for the situation where the system can not generate receipt. | 2021-11-17 | 2021-11-18 | 75% | Jevon Cowell , George Lopez
33 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Create Use Case Specification | 2021-11-06 | 2021-11-18 | 100% | Maisha Masnoon
34 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Create Test Case for core functionality | 2021-11-11 | 2021-11-18 | 100% | Mady Dembele
35 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Create Test Case for GUI | 2021-11-11 | 2021-11-18 | 100% | Mady Dembele
36 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Create Test Case for Calculation | 2021-11-11 | 2021-11-18 | 100% | Mady Dembele
37 | R2 - I4 | 05. Shopping Cart | 5.07 | Generate receipts | Create Test Case for Connectivity | 2021-11-12 | 2021-11-18 | 100% | Mady Dembele
38 | R2 - I5 | 05. Shopping Cart | 5.07 | Generate receipts | Create Test Case for Data Flow In | 2021-11-13 | 2021-11-18 | 100% | Mady Dembele
39 | R2 - I6 | 05. Shopping Cart | 5.07 | Generate receipts | Create Test Case for Exception Handling | 2021-11-14 | 2021-11-18 | 100% | Mady Dembele
40 | R2 - I3 | 05. Shopping Cart | 5.07 | Generate receipts | Execute test cases and document the test execution log | 2021-11-13 | 2021-11-18 | 100% | Maisha Masnoon
41 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Implement Core Functionality | 2021-11-16 | 17/16/2021 | 70% | Jevon Cowell , George Lopez
42 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Implement GUI | 2021-11-16 | 17/16/2021 | 80% | Jevon Cowell , George Lopez
43 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Security: Sensitive data sent will be hashed for data transit | 2021-11-16 | 17/16/2021 | 0% | Jevon Cowell , George Lopez
44 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Field Validation: User's input must fufill the requirements | 2021-11-16 | 17/16/2021 | 80% | Jevon Cowell , George Lopez
45 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Calculation: The prices of user's purchased items must be calculated correctly | 2021-11-16 | 17/16/2021 | 0% | Jevon Cowell , George Lopez
46 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Connectivity: Changes the behavior of the system in case the front end is disconnected from the back end | 2021-11-16 | 17/16/2021 | 80% | Jevon Cowell , George Lopez
47 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Data Flow In: Ensure the data is flowing into Checkout Order Core Feature | 2021-11-16 | 17/16/2021 | 80% | Jevon Cowell , George Lopez
48 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Data Flow Out: Ensure the data is flowing to the database | 2021-11-16 | 17/16/2021 | 80% | Jevon Cowell , George Lopez
49 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Cache: User's order information should be saved in cache | 2021-11-16 | 17/16/2021 | 0% | Jevon Cowell , George Lopez
50 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Crosscut Exception Handling: exception thrown if the checkout cannot be performed | 2021-11-16 | 17/16/2021 | 0% | Jevon Cowell , George Lopez
51 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Use Case Specification | 2021-11-06 | 2021-11-09 | 100% | Tianqi Han
52 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Core functionality | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
53 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for GUI | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
54 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Security | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
55 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Field Validation | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
56 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Calculations | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
57 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Connectivity | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
58 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Data Flow In | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
59 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Data Flow Out | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
60 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Cache | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
61 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Create Test Case for Exception Handling | 2021-11-13 | 2021-11-16 | 100% | Tianqi Han
62 | R2 - I3 | 05. Shopping Cart | 5.08 | Checkout Order | Execute test cases and document the test execution log | 2021-11-16 | 2021-11-16 | 100% | Maisha Masnoon