## I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Implement Core Functionality | 2021-10-08 | 2021-10-15 | 50% | Jevon Cowell, George Lopez
2 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Implement GUI | 2021-10-08 | 2021-10-15 | 50% | Jevon Cowell, George Lopez
3 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Crosscut Security: User input must be sanitized. Sensitive data sent will be hashed for data transit. | 2021-10-08 | 2021-10-15 | 0% | Jevon Cowell, George Lopez
4 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Crosscut Field Validation: User input must fufill requirements. UI will check if inputs match criteria. And show error if not. | 2021-10-08 | 2021-10-15 | 0% | Jevon Cowell, George Lopez
5 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Crosscut Cache: previous entries will be saved in cache. | 2021-10-08 | 2021-10-15 | 0% | Jevon Cowell, George Lopez
6 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Crosscut Exception Handle: exceptions thrown and logged if form post is successful. | 2021-10-08 | 2021-10-15 | 0% | Jevon Cowell, George Lopez
7 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Create Test Case for Core functionality | 2021-10-08 | 2021-10-15 | 100% | Vihan Parmar
8 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Create Test Case for Cross Cutting Concerns | 2021-10-08 | 2021-10-15 | 100% | Vihan Parmar, Roneil Boodram
9 | R1 - I1 | 03. End Users Account | 3.1 | Update an account | Execute test cases and document the test execution log | 2021-10-08 | 2021-10-15 | 0% | Jevon Cowell
10 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Implement Core Functionality | 2021-10-08 | 2021-10-20 | 100% | Jevon Cowell, George Lopez
11 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Implement GUI | 2021-10-08 | 2021-10-20 | 100% | Jevon Cowell, George Lopez
12 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Crosscut Cache: User account cache data should be removed. | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
13 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Crosscut Exception Handle: exception thrown if account cannot be deleted due to varying factors | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
14 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Create Test Case for Core functionality | 2021-10-08 | 2021-10-15 | 100% | Vihan Parmar
15 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Create Test Case for Cross Cutting Concerns | 2021-10-08 | 2021-10-15 | 100% | Lang Gong, Mady Dembele
16 | R1 - I1 | 03. End Users Account | 3.2 | Delete an account | Execute test cases and document the test execution log | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell
17 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Implement Core Functionality | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
18 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Implement GUI | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
19 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Crosscut Security: user input must be sanitized. Sensitive data sent will be hashed for data transit. | 2021-10-08 | 2021-10-15 | 80% | Jevon Cowell, George Lopez
20 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Crosscut Field Validation: User must input username, valid password and other required info. UI will provide feedback on successful or unsuccessful entries. | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
21 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Crosscut Cache: Previous field entries will be saved in cache. | 2021-10-08 | 2021-10-15 | 80% | Jevon Cowell, George Lopez
22 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Crosscut Exception Handle: Exceptions are thrown and logged for form post. | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
23 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Create Test Case for Core functionality | 2021-10-08 | 2021-10-15 | 100% | Vihan Parmar
24 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Create Test Case for Cross Cutting Concerns | 2021-10-08 | 2021-10-15 | 100% | Maisha Masnoon, Tianqi Han
25 | R1 - I1 | 03. End Users Account | 3.3 | Sign up | Execute test cases and document the test execution log | 2021-10-08 | 2021-10-15 | 95% | Jevon Cowell
26 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Implement Core Functionality | 2021-10-08 | 2021-10-15 | 80% | Jevon Cowell, George Lopez
27 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Implement GUI | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
28 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Crosscut Security: user input must be sanitized. User password must fulfill security requirements. And sensitive data sent will be hashed. | 2021-10-08 | 2021-10-15 | 80% | Jevon Cowell, George Lopez
29 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Crosscut Field Validation: user must input username, valid password and other required info. UI will provide feedback on successful or unsuccessful entries. | 2021-10-08 | 2021-10-15 | 100% | Jevon Cowell, George Lopez
30 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Crosscut Cache: previous entries will be saved in cache. | 2021-10-08 | 2021-10-15 | 80% | Jevon Cowell, George Lopez
31 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Crosscut Exception Handle: exception thrown for unexpected input | 2021-10-08 | 2021-10-15 | 80% | Jevon Cowell, George Lopez
32 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Create Test Case for Core functionality | 2021-10-08 | 2021-10-15 | 100% | Vihan Parmar
33 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Create Test Case for Cross Cutting Concerns | 2021-10-08 | 2021-10-15 | 100% | Vihan Parmar, Roneil Boodram
34 | R1 - I1 | 03. End Users Account | 3.4 | Sign In | Execute test cases and document the test execution log | 2021-10-08 | 2021-10-15 | 95% | Jevon Cowell
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59

## I2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Implement Core Functionality | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell, George Lopez
2 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Implement GUI | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell, George Lopez
3 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Crosscut Security: User input must be sanitized. Sensitive data sent will be hashed for data transit. | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell, George Lopez
4 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Crosscut Field Validation: User input must fufill requirements. UI will check if inputs match criteria. And show error if not. | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell, George Lopez
5 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Crosscut Cache: previous entries will be saved in cache. | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell, George Lopez
6 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Crosscut Exception Handle: exceptions thrown and logged if form post is successful. | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell, George Lopez
7 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Create Test Case for Core functionality | 2021-10-25 | 2021-10-27 | 100% | Vihan Parmar
8 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Create Test Case for Cross Cutting Concerns | 2021-10-25 | 2021-10-27 | 100% | Vihan Parmar, Roneil Boodram
9 | R1 - I2 | 03. End Users Account | 3.1 | Update an account | Execute test cases and document the test execution log | 2021-10-25 | 2021-10-27 | 100% | Jevon Cowell
10 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Research Payment APIs | 2021-10-24 | 2021-10-29 | 100% | Jevon Cowell, George Lopez
11 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Implement Core Functionality | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
12 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Implement GUI | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
13 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Crosscut: Security Ensure Credit Card Details are sent to Third Party API under encrypted transit Ensure Credit Card Fields cannot be SQL injected and meet Credit Card data criteria | 2021-10-29 | 2021-11-02 | 50% | Jevon Cowell, George Lopez
14 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Crosscut: Field Validation Ensures field adheres to Credit Card Field Requirments, size, and format | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
15 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Crosscut: Data Flow Out Ensure data is flowing to Process Payment Core Feature | 2021-10-29 | 2021-11-02 | 0% | Jevon Cowell, George Lopez
16 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Crosscut: Cache Ensure Payment ID for payment credentials is cached instead of repeatedly called | 2021-10-29 | 2021-11-04 | 100% | Jevon Cowell, George Lopez
17 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Crosscut: Exception Handling Ensure to handle unexpected or wierd API responses from Payment Processing Vendor | 2021-10-29 | 2021-11-04 | 100% | Jevon Cowell, George Lopez
18 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Create Test Case for functionality | 2021-10-29 | 2021-11-02 | 100% | Vihan Parmar
19 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Create Test Case for Field Validation | 2021-10-29 | 2021-11-02 | 100% | Vihan Parmar
20 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Create Test Case/DFD for Data Flow out | 2021-10-29 | 2021-11-02 | 100% | Vihan Parmar
21 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Create Test Case/DFD for Data Flow in | 2021-10-29 | 2021-11-02 | 100% | Vihan Parmar
22 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Create Test Case for Cache | 2021-10-29 | 2021-11-02 | 100% | Vihan Parmar
23 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Create Test Case for Exception Handling | 2021-10-29 | 2021-11-02 | 100% | Vihan Parmar
24 | R1 - I2 | End Users Accounts | 3.06 | Create Payment Infomation | Execute Test Cases and document the Test Execution Log | 2021-10-29 | 2021-11-02 | 100% | Tianqi Han, Maisha Masnoon
25 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Implement Core Functionality | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
26 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Implement GUI | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
27 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Crosscut: Security Ensure Credit Card Details are sent to Third Party API under encrypted transit Ensure Credit Card Fields cannot be SQL injected and meet Credit Card data criteria | 2021-10-29 | 2021-11-02 | 50% | Jevon Cowell, George Lopez
28 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Crosscut: Field Validation Ensures field adheres to Credit Card Field Requirments, size, and format | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
29 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Crosscut: Data Flow Out Ensure data is flowing to Process Payment Core Feature | 2021-10-29 | 2021-11-02 | 0% | Jevon Cowell, George Lopez
30 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Crosscut: Cache Ensure Payment ID for payment credentials is cached instead of repeatedly called | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
31 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Crosscut: Exception Handling Ensure to handle unexpected or wierd API responses from Payment Processing Vendor | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
32 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Create Test Case for functionality | 2021-10-29 | 2021-11-02 | 100% | Roneil Boodram
33 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Create Test Case for Field Validation | 2021-10-29 | 2021-11-02 | 100% | Roneil Boodram
34 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Create Test Case/DFD for Data Flow out | 2021-10-29 | 2021-11-02 | 100% | Roneil Boodram
37 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Create Test Case for Cache | 2021-10-29 | 2021-11-02 | 100% | Roneil Boodram
38 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Create Test Case for Exception Handling | 2021-10-29 | 2021-11-02 | 100% | Roneil Boodram
39 | R1 - I2 | End Users Accounts | 3.07 | Update Payment Infomation | Execute Test Cases and document the Test Execution Log | 2021-10-29 | 2021-11-02 | 100% | Tianqi Han, Maisha Masnoon
40 | R1 - I2 | End Users Accounts | 3.08 | Delete Payment Infomation | Implement Core Functionality | 2021-10-29 | 2021-11-02 | 50% | Jevon Cowell, George Lopez
41 | R1 - I2 | End Users Accounts | 3.08 | Delete Payment Infomation | Implement GUI | 2021-10-29 | 2021-11-02 | 50% | Jevon Cowell, George Lopez
42 | R1 - I2 | End Users Accounts | 3.08 | Delete Payment Infomation | Crosscut: Entitlement Registered Users can Delete Payment Information from their account | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
43 | R1 - I2 | End Users Accounts | 3.08 | Delete Payment Infomation | Create Test Case for functionality | 2021-10-29 | 2021-11-02 | 100% | Mady Dembele
44 | R1 - I2 | End Users Accounts | 3.08 | Delete Payment Infomation | Create Test Case for entitlement checking | 2021-10-29 | 2021-11-02 | 100% | Mady Dembele
45 | R1 - I2 | End Users Accounts | 3.08 | Delete Payment Infomation | Execute Test Cases and document the Test Execution Log | 2021-10-29 | 2021-11-02 | 100% | Jevon Cowell, George Lopez
46 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Implement Core Functionality | 2021-10-29 | 2021-11-05 | 50% | Jevon Cowell, George Lopez
47 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Implement GUI | 2021-10-29 | 2021-11-05 | 100% | Jevon Cowell, George Lopez
48 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Crosscut: Field Validation Ensure the field adheres to size limit and text format | 2021-10-29 | 2021-11-05 | 25% | Jevon Cowell, George Lopez
49 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Crosscut: Exception Handling Deal with unintended Input and minimum character count | 2021-10-29 | 2021-11-05 | 25% | Jevon Cowell, George Lopez
50 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Create Test Case for functionality | 2021-10-30 | 2021-11-03 | 100% | Tianqi Han, Maisha Masnoon
51 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Create Test Case for field validation | 2021-10-30 | 2021-11-03 | 100% | Tianqi Han, Maisha Masnoon
52 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Create Test Case for Exception Handling | 2021-10-30 | 2021-11-03 | 100% | Tianqi Han, Maisha Masnoon
53 | R1 - I2 | End Users Accounts | 3.1 | Rate Purchased Items | Execute Test Cases and document the Test Execution Log | 2021-10-30 | 2021-11-03 | 100% | Tianqi Han, Maisha Masnoon
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!