## Functional Decomposition
Functional Decomposition
Module Name | Brief Description
01. Digital Banners & Coupons | The main objective of this module is to generate ads across the application through banners and coupons. It will allow the advertisement management team to create and modify any necessary content for the ads. Coupons will also promote any sales or offers provided by our application or the registered stores.
02. Help Desk | This module is to offer both tecnical support and customer support for all the end users, it can troubleshoot technical issues, as well as open / close tickets to handle customer complaints.
03. End-User Account | End-User Account module is compound of the following functionality: register, sign-in/sign-out an account, modify end-user general information, modify favorite store information, search for specific items or stores in the menu bar, subscribe/unsubscribe a plan, review saved stores and purchase history, comment and rate purchased items, contact customer support. In order to pay, every user will be required to sign in.
04.Customize Deliveries | This module of Carriage is mainly responsible for helping vendors locate drivers, helping drivers notify end users about their delivery details, managing a pool of drivers and as a consequence, add convenience across the process.In order to make the process convenient for the vendors, delivery drivers system helps vendors locate drivers with respect to how far are they, how much time will the drivers take to pick up the products from vendors, etc. The delivery drivers system manages a pool of drivers with respect to the number of drivers in and around the vicinity.The delivery drivers system helps drivers notify the end users with regards to their order pick up time and delivery time.
05. Shopping Cart | This module will alllow all who use the Carriage app to receive payments in a fast, effective, user-friendly manner (Vendors, drivers, and external stakeholders, etc.). Various forms of payment/reception of payment (i.e. credit cards, Paypal) will be accepted and can be changed by the end-user, vendor, or driver directly via the app on the GUI. Also this module allows customers to add multiple order to the cart, modify the cart and check out to processing the orders from the cart. In addition, end-users can review the overall order history.
06 .Maps | Utilizing Apple's Mapkit and Google's Maps API, the Map System Module will allow end-users to track the location of their orders from preperation to delivery in real time. The module will also allow end-users to disocver local vendors. Driver-side, the Map System Module will provide Drivers with navigation to vendors and end-users provided address.

## RTM
Requirements Traceability Matrix. Carriage Mobile Application
[6 empty] | 01. Digital Banners & Coupons |  |  | 02. Help Desk |  |  |  | 03. End-User Account | [12 empty] | 04. Customize Deliveries |  | 05. Shopping Cart | [7 empty] | 06. Maps
|  | 01.01 Create banners | 01.02 Update banners | 01.03 Remove banners | 01.04 Create Coupons | 01.05 Update Coupons | 01.06 Remove Coupons | 01.07 Promote new vendors | 02.01 Troubleshoot technical issues | 02.02 Generate open tickets | 02.03 Generate close tickets | 02.04 Communicate with customers | 03.01 Update an account | 03.02 Delete an account | 03.03 Sign up | 03.04 Sign In | 03.05 Sign Out | 03.06 Create Payment Information | 03.07 Update Payment Information | 03.08 Delete Payment Information | 03.09 Review order history | 03.10 Rate purchased items | 3.11 Upgrade to member account | 3.12 Downgrade from member account | 3.13 Connect to support service | 04.01 Plan and coordinate deliveries | 04.02 Troubleshoot delivery issues | 05.01 Track items for orders | 05.02 Manage Orders(make edits) | 05.03 Cancel order | 05.04 Bookmark an Item | 05.05 Save A Store to Favorites | 05.06 Process payments | 05.07 Generate receipts | 05.08 Checkout Order | 06.01 In-App Navigation | 06.02 View Local vendors in the vicinity | 06.03 Order tracking
4.1.1 Advertisement Sales Management | 4.1.1.1 Ability to log in
| 4.1.1.2 Ability to generate ads on the web application | X |  |  | X
| 4.1.1.3 Ability to maintain content of an ad |  | X |  |  | X
| 4.1.1.4 Ability to create contents of digital banners and coupons | X | X |  | X | X
| 4.1.1.5 Ability to finalize the pricing of ads | X | X |  | X | X
| 4.1.1.6 Ability to filter ads content |  | X |  |  | X
| 4.1.1.7 Ability to keep ads up to date |  | X |  |  | X
| 4.1.1.8 Ability to do market research on different advertisement sales techniques | [6 empty] | X
| 4.1.1.9 Ability to build and execute social media strategy through competitive research | [6 empty] | X | [13 empty] | X
4.1.1.10 Ability to understand product performance
| 4.1.1.11 Ability to promote sponsored posts | [6 empty] | X
| 4.1.1.12 Ability to strategize and maintain any social media campaign | [6 empty] | X | [13 empty] | X
4.1.2 User Support Team | 4.1.2.1 Ability to troubleshoot technical issues | [7 empty] | X |  |  | X | [12 empty] | X |  | X | [6 empty] | X | X | X | X | X
| 4.1.2.2 Ability to create customer service tickets and resolve customer complaints | [8 empty] | X | X | X | [12 empty] | X
| 4.1.2.3 Ability to facilitate the communication between end users | [10 empty] | X | [12 empty] | X
4.1.3 Delivery Management | 4.1.3.1 Ability to log in | [28 empty] | X | X |  |  | X | X
| 4.1.3.2 Ability to send the confirmation that order is being prepared | [23 empty] | X |  |  |  |  | X |  |  |  | X | X | X |  | X
| 4.1.3.3 Ability to send the confirmation that the order is ready for delivery | [19 empty] | X |  |  |  | X |  |  |  |  | X |  |  |  | X | X |  |  | X
| 4.1.3.4 Ability to send the tracking number when order is shipped | [19 empty] | X |  |  |  | X |  |  |  |  | X |  |  |  | X | X |  |  | X
| 4.1.3.5 Ability to send the confirmation that the order was delivered | [19 empty] | X |  |  |  | X | [12 empty] | X
| 4.1.3.6 Ability to submit the price per subscription plan | [21 empty] | X | [6 empty] | X |  |  |  | X | X
| 4.1.3.7 Ability to manage the containers of the specific subscription plan | [21 empty] | X | [6 empty] | X |  |  |  | X | X
4.1.4 Participating Grocery Stores Requirement | 4.1.4.1 Ability to log in
| 4.1.4.2 Ability to put items for sale on the store page | X |  |  | X
| 4.1.4.3 Ability to discontinue the sale of items |  |  | X |  |  | X
| 4.1.4.4 Ability to update product information (images, descriptions, prices, etc.) |  | X |  |  | X
| 4.1.4.5 Ability to change the status of items (in stock, out of stock) |  | X |  |  | X | [31 empty] | X
4.1.4.6 Ability to receive customer orders
| 4.1.4.7 Ability to send the confirmation that order is being prepared | [36 empty] | X
| 4.1.4.8 Ability to see order information and delivery person information | [24 empty] | X | [11 empty] | X
| 4.1.4.9 Ability to see and respond to customer comments |  |  |  | X
4.1.4.10 Ability to cancel account
4.1.5 Unregister Customers Requirement | 4.1.5.1 Ability to browse vendors | [6 empty] | X | [28 empty] | X
| 4.1.5.2 Ability to browse vendor listings | [6 empty] | X
| 4.1.5.3 Ability to view local vendors | [35 empty] | X
| 4.1.5.4 Ability to create an account | [13 empty] | X
4.1.6 Register Customers requirements | 4.1.5.1 Ability to create an account | [13 empty] | X
| 4.1.5.2 Ability to delete the account | [12 empty] | X
| 4.1.5.3 Ability to modify the account information | [11 empty] | X |  |  |  |  | X | X | X
| 4.1.5.4 Ability to restore the password/user ID details | [23 empty] | X
| 4.1.5.5 Ability to sign in to (sign out from) already created account | [14 empty] | X | X
| 4.1.5.6 Ability to select the subscription plan | [21 empty] | X
| 4.1.5.7 Ability to pause the subscription plan | [22 empty] | X
| 4.1.5.8 Ability to read the product information | [19 empty] | X | X | [14 empty] | X | X
4.1.5.9 Ability to add/remove items to/from the subscribed box
| 4.1.5.10 Ability to cancel the order before it is prepared for shipping | [19 empty] | X
| 4.1.5.11 Ability to create profile of liked/disliked ingredients | [20 empty] | X
| 4.1.5.12 Ability to skip a future order delivery | [19 empty] | X | [10 empty] | X |  | X | X
| 4.1.5.13 Ability to view the orders history | [19 empty] | X | [8 empty] | X | X | [6 empty] | X
4.1.5.14 Ability to enter/modify the delivery address
| 4.1.5.15 Ability to provide the additional delivery instructions | [28 empty] | X
| 4.1.5.16 Ability to enter/modify the payment information | [27 empty] | X |  | X | [6 empty] | X
| 4.1.5.17 Ability to submit the form to customer support | [23 empty] | X |  |  |  |  | X | X
| 4.1.5.18 Ability to read the resolution of the opened ticket with customer support team | [23 empty] | X |  |  |  |  | X | X
| 4.1.5.19 Ability to share the product on social media | [19 empty] | X | X | [7 empty] | X
| 4.1.5.20 Ability to make product favorite | [19 empty] | X | X
| 4.1.5.21 Ability to view the list of favorite products | [19 empty] | X | X | [9 empty] | X | X | X | X |  | X | X
| 4.1.5.22 Ability to leave the reviews | [19 empty] | X | X | [9 empty] | X | X | X |  |  |  | X
| 4.1.5.23 Ability to rate the products | [20 empty] | X | [15 empty] | X
4.1.7 Registered Deliverers Requirements | 4.1.6.1 Ability to create an account | [7 empty] | X
4.1.6.2 Ability to modify the account information
| 4.1.6.3 Ability to restore the password/user ID details | [7 empty] | X | X
| 4.1.6.4 Ability to sign in to (sign out from) already created account | [8 empty] | X
| 4.1.6.5 Ability to receive customer orders from participating Grocery Stores | [21 empty] | X |  | X |  |  |  |  | X | [7 empty] | X
| 4.1.6.6 Ability to accept or decline orders | [21 empty] | X | [5 empty] | X
| 4.1.6.7 Ability to accept multiple customer orders form the same store. | [23 empty] | X | [10 empty] | X
| 4.1.6.8 Ability to interact with customers and grocery store for orders clarification & statuses | [26 empty] | X | X | X | X | X |  | X | X
| 4.1.6.9 Ability to view your delivery history | [10 empty] | X | [16 empty] | X | [6 empty] | X | X | X
| 4.1.6.10 Ability to leave Deliverers reviews | [24 empty] | X | X
4.1.6.11 Ability to delete the account

## Crosscut Description
x | Descriptions | Test Ideas
SEC - Security (Roneil) | This concern relates to ensuring that end-user/driver/vendor data is secure from data breaches in all forms. | Ethical hacking tests (penetration tests). Testing multi-factor authentication for end-users. Encrypted passcodes.
LA - Location accuracy (Roneil) | This concern relates to ensuring that the location of driver/vendor/end-user are accurately reflected on mapping system. | Perform a test of a food order placed by a test end-user, with vendor and driver to monitor location accuracy in real-time
PP - Payment processing (Roneil) | This concern relates to ensuring that the payment processing system accurately debits/credits all end-users/vendors/drivers accurately; this applies to payments and refunds issued. | Perform a test of a food order payment (and request for refund) to ensure accurate debit/credit is reflected as needed in application and bank statements
ET - Entitlements (George) | This concern relates to different internal user access privileges (roles) and how they impact the behavior of core features. List of User Roles: members and guests | Limit access of user priverliges based on roles, member vs guest. For instance must sign in/sign up to place order. Only Admin login into inventory can alter inventory information.
FV - Field Validation (George) | This concern relates to validating individual data entry fields | Only admin of a paticular store can alter inventory info for grocery DB. All entries must be made via forms with proper validation of input data. Limit amount of user inputs fields.
DDV - Data-Dependency Validation (George) | This concern relates to validating field value combinations. It also includes validation of constrains, for example, a currency cannot be make inactive if it has outstanding orders/trades | Data must be validated on three fronts: UI, Middleware and Database. Required Fields and data types must be inplace. Account standing and credit card validation prior to order confirmation.
DDD - Data-Driven Defaults (George) | This concern relates to populating field default values based on another field value | Last purchase notification. Order History for user convenience. check HTML autocomple for input fileds
CL - Calculations (George) | This concern represents various "behind-the-screen" calculations that are executed in the context of core features | test effectiveness of methods for User Valdiation.. Payment validation. Fraud detection.
CC - Concurrency (George) | This concern relates to simultaneous data manipulation by more than one user. For example, both users see the same order. User 1 tries to modify this order, whereas User 2 tries to execute this order | Ensure shopping cart persistence. and session handling.
CN - Connectivity (George) | This concern relates to the architecture of an application where the front-end can be disconnected from the back end and that would change the behavior of some core features | implementing serverless optimizations, test to ensure app works without wifi connection
DF-In - Data Flow In (Jevon) | This concern addresses the core feature behavior when it takes data in from another core feature of the same application | Implement Data Flow Testing to find events that can interupt data inflow
DF-Out - Data Flow Out (Jevon) | This concern addresses the core feature behavior when it generates data used by other core feature(s) of the same application | Implement Data Flow Testing to find events that can interupt data outflow and if generated data is as intended.
SI-In System Interface (inbound) (Jevon) | This concern relates to data coming from external applications and indicates which of the core features consume such data. Including this concern can help a team to better plan E2E testing and analyze the impact of changes from other applications | A dummy system can be implemented to ensure that data that's meant to be received is sanatized, meet what's expected, doesn't bring down parts of or the whole application, and is proccessed and inserted where ti would be in the live application.
SI-Out - System Interface (outbound) (Jevon) | This concern relates to data passed to external applications and indicates which of the core features generate such data. Including this concern can help a team to better plan E2E testing and analyze the impact of changes on other applications | A dummy system can be implemented to ensure that data that's meant to be sent is not altered or corrupted and is successfully inserted where it should. Simulations of unexpected events (such as power outages or network downage) can be done to ensure that the system follows Consisistency and Durability properties.
CA - Cache (Jevon) | Concerns non-core-feature data flow in. For example, static data cached in the component is a concern but is does not flow into the component as part of a trade booking. | implementation of debugging tools to see data saved to cache. This will allow develoeprs and testers to see if data is being cached correctly or at all
ExH - Exception Handling (Maisha) | This concern relates to any exception handling (raising of exception) or rejection of trade/wire. | Ensuring that useful error message should be given to the UI instead of accumulating all the exceptions.
PF - Performance (Roneil) | This concern relates to performance requirements affecting some of the core features. | Conduct a test order and determine if app runs timely without delays in flow within system interfaces
LOC - Localization (Tianqi) | This concern relates to ensuring that core features are usable in different lanaguages and regions | Adding some commonly used languages and region information to the system settings, testing to ensure that the app can adapt to different languages and regions.
A11Y - Accessiblity (Tianqi) | This concern relates to ensuring that core features are usable to users with disbailities. | Adding several special functions to the system settings that can help the disbailities to use the app better.
LOG - Logging (Tianqi) | This concern relates to ensuring that internal and external actions are recorded to understand and diagnose problems | Implementing the tracking systems in the app to supervise internal and external actions, and ensuring that these actions can be compiled and edited.

## I1, I2 RCT Details
Iteration 1
Iteration 2
Iteration 3
Iteration 4
features implemented last semester
Requirements Composition Table. Carriage Mobile Application
List of Concerns | 01. Digital Banners & Coupons | [6 empty] | 02. Help Desk |  |  |  | 03. End-User Account | [12 empty] | 04. Customize Deliveries |  | 05. Shopping Cart | [7 empty] | 06. Maps
| 01.01 Create banners | 01.02 Update banners | 01.03 Remove banners | 01.04 Create Coupons | 01.05 Update Coupons | 01.06 Remove Coupons | 01.07 Promote new vendors | 02.01 Troubleshoot technical issues | 02.02 Generate open tickets | 02.03 Generate close tickets | 02.04 Communicate with customers | 03.01 Update an account | 03.02 Delete an account | 03.03 Sign up | 03.04 Sign In | 03.05 Sign Out | 03.06 Create Payment Information | 03.07 Update Payment Information | 03.08 Delete Payment Information | 03.09 Review order history | 03.10 Rate purchased items | 3.11 Upgrade to member account | 3.12 Downgrade from member account | 3.13 Connect to support service | 04.01 Plan and coordinate deliveries | 04.02 Troubleshoot delivery issues | 05.01 Track items for orders | 05.02 Manage Orders(make edits) | 05.03 Cancel order | 05.04 Bookmark an Item | 05.05 Save A Store to Favorites | 05.06 Process payments | 05.07 Generate receipts | 05.08 Checkout Order | 06.01 In-App Navigation | 06.02 View Local vendors in the vicinity | 06.03 Order tracking | Crosscut Counts
Core Functionality | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | I1 | I1 | I1 | I1 | 1 | I2 | I2 | I2 | I4 | I2 | I4 | I4 | 1 | 1 | 1 | I4 | I3 | I3 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 1
GUI Features | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | I2 | I1 | I1 | I1 | 1 | I2 | I2 | I2 | I4 | I2 | I4 | I4 | 1 | 1 | 1 | I4 | I3 | I3 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 1
Crosscutting Concerns
SEC - Security | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | I2 | 0 | I1 | I1 | 0 | I2 | I2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | I4 | 0 | 0 | 0 | 0 | 1 | I3 | I3 | 1 | 1 | 1 | 18
LA - Location accuracy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 10
PP - Payment processing | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 17
ET- Entitlements | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | I2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 35
FV - Field Validation | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | I2 | I2 | I1 | I1 | 0 | I2 | I2 | 0 | 0 | I2 | I4 | I4 | 1 | 0 | 1 | 0 | I3 | 0 | I4 | I4 | 1 | I3 | I3 | 0 | 1 | 0 | 13
DDV - Data-Dependency Validation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | I4 | I3 | 0 | I4 | I4 | 0 | I3 | I3 | 0 | 0 | 0 | 11
DDD - Data-Driven Defaults | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 13
CL - Calculations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | I4 | I3 | 0 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 0 | 7
CC - Concurrency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 10
CN - Connectivity | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | I4 | I3 | I3 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 1 | 17
DF-In - Data Flow In | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | I2 | I2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | I4 | I3 | 0 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 1 | 8
DF-Out - Data Flow Out | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | I2 | I2 | 0 | 0 | 0 | I4 | I4 | 1 | 1 | 1 | I4 | I3 | I3 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 1 | 18
SI-In System Interface (inbound) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 24
SI-Out - System Interface (outbound) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
CA - Cache | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | I2 | 0 | I1 | I1 | 1 | I2 | I2 | 0 | I4 | 0 | 0 | 0 | 0 | 1 | 1 | I4 | I3 | I3 | I4 | I4 | 1 | I3 | I3 | 1 | 1 | 1 | 14
ExH - Exception Handling | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | I2 | I1 | I1 | I1 | 1 | I2 | I2 | 0 | I4 | I2 | I4 | I4 | 1 | 1 | 1 | I4 | I3 | I3 | 0 | 0 | 1 | I3 | I3 | 1 | 1 | 1 | 19
PF - Performance | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 35
LOC - Localization | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 37
A11Y - Accessiblity | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 37
LOG - Logging | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 37

## Feature Short Description
Module | Core Feature Name | Feature Short Descriptions
01. Digital Banners & Coupons | 01.01 Create Banners | Allows user to create digital banners
| 01.02 Update Banners | Allows the user to modify the contents of any banners
| 01.03 Remove Banners | Allows the user to delete any ads(digital banners)
| 01.04 Create Coupons | Allows the user to generate digital coupons
| 01.05 Update Coupons | Allows the user to modify the contents of any coupons
| 01.06 Remove Coupons | Allows the user to delete any ads(coupons)
| 01.07 Promote new vendors | Allows the user to promote or advertise any new vendors
02. Help Desk | 02.01 Troubleshoot technical issues | This feature allows users to troubleshoot technical issues and provide technical support
| 02.02 Generate open tickets | This feature allows users to generate open tickets
| 02.03 Generate close tickets | This feature allows users to generate close tickets
| 02.04 Communicate with customers | This feature allows users to communicate with customers who have complaints and need support
03. End-User Account | 03.01 Update an account | This feature allows end-user to update an account.
| 03.02 Delete an account | This feature allows end-user to delete an account.
| 03.03 Sign up | This feature allows end-users to sign up for their account.
| 03.04 Sign in | This feature allows end-users to sign in their account.
| 03.05 Sign Out | This feature allows end-users to sign sign out from their account.
| 03.06 Create Payment information | This feature allows users to create payment information
| 03.07 Update Payment information | This feature allows users to update payment information
| 03.08 Delete Payment information | This feature allows users to delete payment information
| 03.09 Review order history | This feature allows users to review order history
| 03.10 Rate purchased items | This feature allows users to rate and comment on the their ordered products
| 03.11 Upgrade to member account | This feature allows users to select a subscription plan and upgrade their account to a member account
| 03.12 Downgrade from member account | This feature allows users to pause and cancel their subscription plan.
| 03.13 Connect to support service | This feature allows users to connect to the support team to handle complaints and any other issues
04. Customize Deliveries | 04.01 Plan and coordinate deliveries | This feature gives user's the ability to navigate to an order's vendor which ensures timely and accurate customer deliveries
| 04.02 Troubleshoot delivery issues | This feature gives user's the ability to solve queries encounter by drivers
05. Shopping Cart | 05.01 Track items for orders | Customers can view the status of their order (pending, approved and waiting for pickup from deliver, ETA , and delivery confirmation
| 05.02 Manage Orders(make edits) | Customers can edit or update orders as needed in the cart
| 05.03 Cancel order | Allows the customers to cancel orders
| 05.04 Bookmark an Item | Customers can bookmark an item that they would like to consider for purchase at a later time
| 05.05 Save A Store to Favorites | Customer can add specific stores/vendors to their favorites list and view that list
| 05.06 Process payments | Allows all who use the Carriage app to receive payments in a fast, effective, user-friendly manner and also. Various forms of payment/reception of payment (i.e. credit cards, Paypal) will be accepted and can be changed by the end-user, vendor, or driver directly via the app on the GUI.
| 05.07 Generate receipts | Allows the user (Vendors, drivers, and external stakeholders, etc.) to generate receipts.
| 05.08 Checkout Order | Allows the user to checkout their order for delivery
06. Maps | 06.01 In-App Navigation | This feature gives drivers navigation to an order's vendor and end-user
| 06.02 View Local vendors in the vicinity | This feature allows a user to view and search local vendors in their area
| 06.03 Order tracking | Customers can view, bookmark and obtain receipts all current & previous their orders. Live Orders can be tracked on a live map from order preparation to delivery.

## ET-Entitlements
User Roles | 01. Digital Banners & Coupons | [6 empty] | 02. Help Desk |  |  |  | 03. End-User Account | [12 empty] | 04. Customize Deliveries |  | 05. Shopping Cart | [7 empty] | 06. Maps
| 01.01 Create banners | 01.02 Update banners | 01.03 Remove banners | 01.04 Create Coupons | 01.05 Update Coupons | 01.06 Remove Coupons | 01.07 Promote new vendors | 02.01 Troubleshoot technical issues | 02.02 Generate open tickets | 02.03 Generate close tickets | 02.04 Communicate with customers | 03.01 Update an account | 03.02 Delete an account | 03.03 Sign up | 03.04 Sign In | 03.05 Sign Out | 03.06 Create Payment Information | 03.07 Update Payment Information | 03.08 Delete Payment Information | 03.09 Review order history | 03.10 Rate purchased items | 3.11 Upgrade to member account | 3.12 Downgrade from member account | 3.13 Connect to support service | 04.01 Plan and coordinate deliveries | 04.02 Troubleshoot delivery issues | 05.01 Track items for orders | 05.02 Manage Orders(make edits) | 05.03 Cancel order | 05.04 Bookmark an Item | 05.05 Save A Store to Favorites | 05.06 Process payments | 05.07 Generate receipts | 05.08 Checkout Order | 06.01 In-App Navigation | 06.02 View Local vendors in the vicinity | 06.03 Order tracking
Unregister Customer | [13 empty] | X | [14 empty] | X | [6 empty] | X
Register Customers | [7 empty] | X |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  | X | X | X | X | X | X | X | X |  | X | X
Register Stores | X | X | X | X | X | X | X | X |  | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | X | X | X | X | X | X |  |  | X | X |  |  | X
Register Deliverers | [7 empty] | X |  | X | X | X | X | X | X | X |  |  |  | X |  |  |  |  | X | x | [8 empty] | X | X | X
User Support Team | X | X | X | X | X | X | X | X | X | X | X | [12 empty] | X | X | X | X | X | X | X |  |  | X | X | X | X | X
Advertisement Sales Representatives | x | x | x | x | x | x | x | [25 empty] | X
Delivery Management Representative | [21 empty] | X |  | X | X | X | X | X | X | X | X | X | X |  | X |  | X
Pricing optimization & final ad rate analyst | [32 empty] | X
Digital Advertising Management Specialist | [6 empty] | X | [25 empty] | X
Market Researcher | [32 empty] | X