## Road Map
Food Delivery Application (Carriage) - Road Map
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/15 | Iteration 2 - 11/5 | Iteration 3 - 11/19 | Iteration 4 - 12/17
Module 1 - Digital Banners and Coupons | 01.01 Create banners
| 01.02 Update banners | [5 empty] | features implemented last semester
| 01.03 Remove banners | [5 empty] | Iteration 1
| 01.04 Create Coupons | [5 empty] | Iteration 2
| 01.05 Update Coupons | [5 empty] | Iteration 3
| 01.06 Remove Coupons | [5 empty] | Iteration 4
01.07 Promote new Vendors
Module 2 - Help Desk | 02.01 Troubleshoot technical issues
02.02 Generate open tickets
02.03 Generate close tickets
02.04 Communicate with customers
Module 3 - End-User Account | 03.01 Update an account | 4 | x
| 03.02 Delete an account | 3 | x
| 03.03 Sign up | 2 | x
| 03.04 Sign In | 2 | x
03.05 Sign Out
| 03.06 Create Payment Information | 2 |  | x
| 03.07 Update Payment Information | 2 |  | x
| 03.08 Delete Payment Information | 2 |  | x
| 03.09 Review order history | 3 |  | x
| 03.10 Rate purchased items | 3 |  | x
| 03.11 Upgrade to member account | 1 |  |  |  | x
| 03.12 Downgrade from member account | 1 |  |  |  | x
03.13 Connect to support service
Module 4 - Customize Deliveries | 04.01 Plan and coordinate deliveries
04.02 Troubleshoot delivery issues
Module 5 - Shopping Cart | 05.01 Track items for orders | 4 |  |  |  | x
| 05.02 Manage Orders(make edits) | 3 |  |  | x
| 05.03 Cancel order | 3 |  |  | x
| 05.04 Bookmark an item | 1 |  |  |  | x
| 05.05 Save store to favorites | 1 |  |  |  | x
05.06 Process Payments
| 05.07 Generate receipts | 3 |  |  | x
| 05.08 Checkout Order | 3 |  |  | x
Module 6 - Maps | 06.01 In-App Navigation
06.02 View Local Vendors in the vicinity
06.03 Order Tracking
|  | Velocity : | 11 | 12 | 12 | 8

## Story Map
Epics |  | Food Delivery Application (Carriage) - User Story Map
Epic 1 - Digital Banners and Coupons |  | Epic 1 - Digital Banners and Coupons | Epic 2 - Help Desk | Epic 3 - End-User Account | Epic 4 - Customize Deliveries | Epic 5 - Shopping Cart | Epic 6 - Maps
Epic 2 - Help Desk | User Stories |  |  | 03.01 Update an account
Epic 3 - End-User Account |  |  |  | 03.02 Delete an account
Epic 4 - Customize Deliveries |  |  |  | 03.03. Sign Up
Epic 5 - Shopping Cart |  |  |  | 03.04 Sign In |  |  |  | Iteration 1
Epic 6 - Maps |  |  |  | 03.06 Create Payment Information
03.07 Update Payment Information
03.08 Delete Payment Information
03.09 Review order history
03.10 Rate purchased items
Iteration 2
05.02 Manage Orders(make edits)
05.03 Cancel order
05.07 Generate receipts
[6 empty] | 05.08 Checkout Order |  | Iteration 3
|  |  |  | 03.11 Upgrade to member account |  | 05.01 Track items for orders
|  |  |  | 03.12 Downgrade from member account |  | 05.04 Bookmark an item
05.05 Save store to favorites
Iteration 4
Iteration 1
Iteration 2
Iteration 3
Iteration 4